## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 |  | Introduction to Project,AI,ML and Langchain | MUST HAVE | No Dependency | Yashwanth Balaji | 3- Completed
S2 | S2 |  | Implementation of langchain, langchain memory | MUST HAVE | Gemini API | Yashwanth Balaji | 3- Completed
S3 | S3 |  | RAG - Ingestion, Retrieval, Retrieval using Pinecone | MUST HAVE | Pinecone | Yashwanth Balaji | 3- Completed
S4 | S4 |  | Project | MUST HAVE | No Dependency | Yashwanth Balaji | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | TID-01 | Introduction to Project | 2025-02-24 | 2025-02-25 | Yashwanth Balaji | Others | 3- Completed
US-002 | TID-02 | Implementation of Langchain, Langchain memory | 2025-03-01 | 2025-03-05 | Yashwanth Balaji | Coding | 3- Completed
US-003 | TID-03 | RAG - Ingestion, Retrieval, Retrieval using Pinecone | 2025-03-10 | 2025-03-14 | Yashwanth Balaji | Coding | 3- Completed
US-004 | TID-04 | Project | 2025-03-15 | 2025-03-28 | Yashwanth Balaji | Build | 3- Completed

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Unclear project scope and roadmap | Had a kickoff meeting with mentor and team to define clear objectives and deliverables.
Sprint 2 | Day 7 | Difficulty integrating GeminiAPI with Streamlit | Researched documentation and debugged errors with mentor’s guidance.
Sprint 3 | Day 9 | Database connectivity issue with ChromaDB | Identified the misconfiguration and updated connection settings.
Sprint 4 | Day 12 | Performance lag in chatbot response time | Optimized query processing and reduced unnecessary API calls.
Sprint 5 | Day 18 | Getting errors in speech recognition | Debugged using logs and solved it in a class session with the mentor.
Sprint 6 | Day 24 | Final testing uncovered minor UI glitches | Fixed bugs, enhanced UX, and finalized the project for deployment.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2025-02-24 | 2025-02-28 | Yashwanth Balaji | Understanding project scope, setting up development environment | Working without clear requirements | Conducting research on Langchain & vector databases | Finalized architecture after discussions with mentor & team
2 | 2 | 2025-03-01 | 2025-03-04 | Yashwanth Balaji | Implementing Langchain, Langchain memory | Debugging without structured logs | Implementing session-based memory in chatbot | Optimized memory management and fixed session retention issues
3 | 3 | 2025-03-14 | 2025-03-16 | Yashwanth Balaji | Setting up RAG pipeline, ingestion of documents | Using inefficient vector storage | Optimizing retrieval process with Pinecone | Enhanced search accuracy and fixed retrieval pipeline errors
4 | 4 | 2025-03-24 | 2025-03-28 | Yashwanth Balaji | Finalizing project, integrating all components | Ignoring performance tuning | Testing and deploying chatbot | Successfully deployed and validated chatbot
5
6
7